## Summary
Itrend-Palacio
2025-09-01
[36 empty] | Completed % | 32.0%
|  | Pre | During | Post | Reinforcement | Shuttering | Other | Pre | During | Post | Reinforcement | Shuttering | Other | Pre | During | Post | Reinforcement | Shuttering | Other | Pre | During | Post | Reinforcement | Shuttering | Other | Pre | During | Post | Reinforcement | Shuttering | Other | Pre | During | Post | Reinforcement | Shuttering | Other
1 | CHECKLIST FOR WATERPROOFING Samshield XL 1500 (1 | 1 | 1 | 1 | 0 | 0 | 0 | 10 | 5 | 2 | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 7 | 4 | 0 | 0 | 0
2 | MEP Checklist | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
3 | PCC (PLAIN CEMENT CONCRETE) | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 0
4 | RCC FOOTING WORK | 7 | 7 | 7 | 0 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 16 | 0 | 1 | 0
5 | RCC Works | 22 | 22 | 22 | 1 | 1 | 0 | 44 | 44 | 44 | 3 | 1 | 0 | 29 | 29 | 28 | 1 | 1 | 0 | 7 | 7 | 6 | 0 | 1 | 0 | 5 | 5 | 5 | 0 | 0 | 0 | 107 | 107 | 105 | 5 | 4 | 0
6 | Waterproofing Checklist (Dr | 3 | 2 | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 6 | 5 | 5 | 0 | 0 | 0
7 | TOTAL | 33 | 32 | 32 | 1 | 1 | 0 | 68 | 63 | 60 | 3 | 1 | 1 | 31 | 30 | 29 | 1 | 1 | 4 | 8 | 8 | 7 | 0 | 2 | 0 | 7 | 7 | 7 | 0 | 0 | 1 | 147 | 140 | 135 | 5 | 5 | 6