## CSV-INSTRUCTION-DETAIL-REPORT-0
| I Trend Palacio |  |  |  |  | 2025-09-10
|  | Instructions | Total | Open | Closed | % |  |  | Closed | 1
|  | Previous | 19 | 0 | 19 | 100% |  |  | Open | 0
|  | Today's | 8 | 8 | 0 | 0%
|  | Total | 27 | 8 | 19 | 70.37%
Sr. No. | Project Name | Location / Reference | Description | Recommendation | Raised By | Raised On Date | Raised On Time | Deadline Date | Deadline Time | Type | Tag 1 | Assigned Team | Assigned Team User | Status 26/08/2025
2025-09-10
1 | Itrend Palacio | Itrend-Palacio/Cube regester | Palacio - cube register - updation balance 7th day results - casting date 22/08/2025 | Need to keep the regester updated | Omkar | 2025-09-10 | 18:21 | 2025-09-12 | 18:21 | Documentation poor 1.8.25 |  | Main Team | Lahu Gaikwad (Saheel properties) | RAISED
2 | Itrend Palacio | Itrend-Palacio/Cube regester | Palacio - cube register - casting date 06/08/2025 - M30 - A raft - 28th day report 22.50 MPa - below acceptance limit - as number of cubes cast are 09 nos | Need to test balance 3 cubes for 56 days | Omkar | 2025-09-10 | 18:20 | 2025-09-12 | 18:19 | Documentation poor 1.8.25 |  | Main Team | Lahu Gaikwad (Saheel properties) | RAISED
3 | Itrend Palacio | Itrend-Palacio/RMC regester | Palacio - casting date 06/08/2025 - as per RMC incoming records no issue with concrete timing, temp and slump - seems cube casting issue | Need tk rectify | Omkar | 2025-09-10 | 18:19 | 2025-09-12 | 18:18 | Documentation poor 1.8.25 |  | Main Team | Lahu Gaikwad (Saheel properties) | RAISED
4 | Itrend Palacio | Itrend-Palacio/Cube testing | Palacio - M30 - casting date 06/08/2025 - below acceptance limit on 28th day - 22.50 MPa | Need tk check further for 56 days | Omkar | 2025-09-10 | 18:18 | 2025-09-12 | 18:17 | Documentation poor 1.8.25 |  | Main Team | Lahu Gaikwad (Saheel properties) | RAISED
5 | Itrend Palacio | Itrend-Palacio/Cube regester | Palacio - incomplete register - 28th day register - casting date 02/08/2025 and 03/08/2025 | Need to check | Omkar | 2025-09-10 | 18:17 | 2025-09-12 | 18:16 | Documentation poor 1.8.25 |  | Main Team | Lahu Gaikwad (Saheel properties) | RAISED
6 | Itrend Palacio | Itrend-Palacio/B wing/Cube regester | Palacio - B wing slab casting - 30/08/2025 - cubes cast less than agreed casting frequency - not acceptable | Need tk impart training immediately | Omkar | 2025-09-10 | 18:16 | 2025-09-12 | 18:14 | Documentation poor 1.8.25 |  | Main Team | Lahu Gaikwad (Saheel properties) | RAISED
7 | Itrend Palacio | Itrend-Palacio/C wing/3rd slab | Cup lock supporting done is different from shuttering design, no base plate used. | Shuttering design shall be checked and followed. | Omkar | 2025-09-10 | 12:35 | 2025-09-12 | 11:57 | Workmanship Poor 1.8.25 |  | KRITIJA CONSTRUCTION | Sanchal Kumbhar (Kritija) | RAISED
8 | Itrend Palacio | Itrend-Palacio/C wing/3rd Slab | Suggestion for improvement | Proper care needs to be taken while placing the pipe line chairs it may lead to conduit damages. | Omkar | 2025-09-10 | 12:33 | 2025-09-12 | 12:27 | Supervision Poor 1.8.25 |  | Main Team | Pradnesh Jamkar (Saheel properties) | RAISED
2025-08-26
1 | Itrend Palacio | Itrend-Palacio/C wing/Floor 1/Pour 1/Rear side | wooden supports embedded in chajjah concrete | need to remove and recast with GP2. In future needs to use rebars to support - chairs which get embedded in concrete. | Omkar | 28/08/2025 | 10:28 | 30/08/2025 | 10:24 | Workmanship Poor 1.8.25 |  | Main Team | KIRAN KHAIRNAR (Saheel properties) | CLOSED
2 | Itrend Palacio | Itrend-Palacio/A wing/Floor 1/Pour 1/Between flat 101 and 103 | slump and weight of concrete not checked | each TM shall be checked for weight and weight slip shall be demanded , it shall be randomly checked by site team. Root cause - possibility as M35/M40 - 1st TMs recd at site - probability of washed TMs were not unloaded after overnight washing and the water in TMs may has been added to concrete resulting in extra water in concrete. | Omkar | 26/08/2025 | 17:54 | 28/08/2025 | 17:44 | Material quality Poor 1.8.25 |  | Main Team | KIRAN KHAIRNAR (Saheel properties) | CLOSED
2025-08-12
1 | Itrend Palacio | Itrend-Palacio/B wing/First slab | 31/07/2025 - M35 - RVK - 7th day - 19.50 MPa (55%) - lower side | need to recheck on 14th day | Omkar | 2025-08-12 | 15:27 | 2025-08-14 | 15:26 | Documentation poor 1.8.25 |  | Main Team | Pradnesh Jamkar (Saheel properties) | CLOSED
2 | Itrend Palacio | Itrend-Palacio/C wing/Above Second slab | cover to reinforcement for SW 200/230 mm wide mentioned as 30 mm including links | need to reconfirm from fire protection 2hrs point of view | Omkar | 2025-08-12 | 15:01 | 2025-08-14 | 14:25 | Documentation poor 1.8.25 |  | Main Team | Pradnesh Jamkar (Saheel properties) | CLOSED
3 | Itrend Palacio | Itrend-Palacio/C wing/Second slab casting | RMC TM concrete placement time exceeds the retention time | QAQC engineer to be more vigilant | Omkar | 2025-08-12 | 15:58 | 2025-08-14 | 15:54 | Documentation poor 1.8.25 |  | Main Team | Prashant Mahajan (Saheel properties) | CLOSED
4 | Itrend Palacio | Itrend-Palacio/A wing/Lower Parking/Column abive raft | Concrete placement has exceeded the retention time of 3hrs | QAQC engineer to be more vigilant | Omkar | 2025-08-12 | 15:41 | 2025-08-14 | 15:36 | Supervision Poor 1.8.25 |  | Main Team | Prashant Mahajan (Saheel properties) | CLOSED
5 | Itrend Palacio | Itrend-Palacio/C wing/Second slab | Improper bracing location,tied with binning wires, no clamps used | Couplers shall be used | Omkar | 2025-08-13 | 13:34 | 2025-08-15 | 13:33 | Workmanship Poor 1.8.25 | RCC | KRITIJA CONSTRUCTION | Sanchal Kumbhar (Kritija) | CLOSED
6 | Itrend Palacio | Itrend-Palacio/C wing/Above Second slab | improper workmanship will lead to leakages - ply side stuck in chajjah concrete - mason did not ensure to re remove concrete at side and thapi should have been passed below ply to ensure that it is free | Supervision shall be stringent | Omkar | 2025-08-13 | 13:33 | 2025-08-15 | 13:31 | Supervision Poor 1.8.25 | RCC | KRITIJA CONSTRUCTION | Sanchal Kumbhar (Kritija) | CLOSED
7 | Itrend Palacio | Itrend-Palacio/C wing/Second slab | proper heads opened more than 50% | Shuttering design to be followed | Omkar | 2025-08-13 | 12:59 | 2025-08-15 | 12:46 | Workmanship Poor 1.8.25 | RCC | KRITIJA CONSTRUCTION | Sanchal Kumbhar (Kritija) | CLOSED
8 | Itrend Palacio | Itrend-Palacio/C wing/Above Second slab | reinforcement workmanship issue observ d at many columns - size of link required is 1140 mm whereas on site it is 1150 mm | Recommended workmanship to be followed | Omkar | 2025-08-13 | 12:48 | 2025-08-15 | 12:45 | Workmanship Poor 1.8.25 | RCC | KRITIJA CONSTRUCTION | Sanchal Kumbhar (Kritija) | CLOSED
9 | Itrend Palacio | Itrend-Palacio/C wing/Above Second slab | Size of link requires is 1140 mm but found 1150 mm | RCC workmanship to be followed | Omkar | 2025-08-13 | 12:48 | 2025-08-15 | 12:43 | Workmanship Poor 1.8.25 | RCC | KRITIJA CONSTRUCTION | Sanchal Kumbhar (Kritija) | CLOSED
10 | Itrend Palacio | Itrend-Palacio/C wing/Above second slab | not providing master rings | Master ring should be provided | Omkar | 2025-08-13 | 12:48 | 2025-08-15 | 12:40 | Workmanship Poor 1.8.25 | RCC | KRITIJA CONSTRUCTION | Sanchal Kumbhar (Kritija) | CLOSED
11 | Itrend Palacio | Itrend-Palacio/C wing/Second slab | improper cover - root cause - no cover provided at concrete top level | Master ring to be provided and cover shoupd be provided | Omkar | 2025-08-13 | 12:46 | 2025-08-15 | 12:38 | Workmanship Poor 1.8.25 | RCC | KRITIJA CONSTRUCTION | Sanchal Kumbhar (Kritija) | CLOSED
12 | Itrend Palacio | Itrend-Palacio/C wing/Above Second slab | Master ring not provided and no porper cover provided. | need to provide additional bar at link corners | Omkar | 2025-08-12 | 16:05 | 2025-08-14 | 14:49 | Workmanship Poor 1.8.25 |  | Main Team | Pradnesh Jamkar (Saheel properties) | CLOSED
13 | Itrend Palacio | Itrend-Palacio/C wing/Above Second slab | unfinished / uncompacted at SW bottom - as it is near toilet , need to chip off the loose material - as it will pose leakage issues, need to control | Need to break and clear the uncompacted concrete and ensure proper joint | Omkar | 2025-08-12 | 16:02 | 2025-08-14 | 14:51 | Workmanship Poor 1.8.25 |  | Main Team | Pradnesh Jamkar (Saheel properties) | CLOSED
14 | Itrend Palacio | Itrend-Palacio/C wing/Above Second slab | main bars misaligned | Reinforcement workmanship to be followed | Omkar | 2025-08-12 | 16:01 | 2025-08-14 | 14:47 | Workmanship Poor 1.8.25 |  | Main Team | Pradnesh Jamkar (Saheel properties) | CLOSED
15 | Itrend Palacio | Itrend-Palacio/C wing/Above Second slab | electrical boxes and conduits in SW, box will project outside the surface, conduits running in cover zone will pose issues of cracks as only slurry will reach at conduits | Need to check the gaps between pipes to ensure concrete passes, need to check the area after concreting is done | Omkar | 2025-08-12 | 16:00 | 2025-08-14 | 14:56 | Workmanship Poor 1.8.25 |  | Main Team | Pradnesh Jamkar (Saheel properties) | CLOSED
16 | Itrend Palacio | Itrend-Palacio/C wing/Second slab | shuttering design is available at office, not available at site carpentery supervisor, bracing shall be coupled with couplers only, whereas at site binding wire is used | Shuttering design to be followed | Omkar | 2025-08-12 | 15:31 | 2025-08-14 | 15:30 | Documentation poor 1.8.25 |  | Main Team | Pradnesh Jamkar (Saheel properties) | CLOSED
17 | Itrend Palacio | Itrend-Palacio/A wing/East side raft | 10/07/2025 - RVK - A East raft - M30 - 28th day - 28.50 MPa | need to check further , send a mail to vendor | Omkar | 2025-08-12 | 15:28 | 2025-08-14 | 15:27 | Documentation poor 1.8.25 |  | Main Team | Pradnesh Jamkar (Saheel properties) | CLOSED